**REG.POST. ACK. DUE**

Date: 05-06-2021

To

Sri. Kantha Reddy

Advocate

Off: #6-3-124, 2nd Floor, Shutter No. 205,

Praja Bhavan, Opposite to Z. P. H.S.

Shivarampally, Rajendranagar, R. R. District

Resi: #6-3-71, Near Hanuman Temple,

Shivarampally, Rajendranagar (M), R. R. District.

Sir,

Sub: Under the instructions of my client M/s. Telangana State Southern Power Distribution Company Limited (TSSPDCL) represented by the Superintending Engineer, Operations, Secunderabad Circle, I address you the following reply notice to the legal notice issued by you dated 21-04-2021 on behalf of M/s. Ranjana Electrical Works and Contractors.

The allegations made in the legal notice by your client against the officials of TSSPDCL, more specifically the Superintending Engineer Mr. C. Madhav Reddy are totally false and have been made with an intention to coerce and threaten the officials to heed to your clients illegal and unlawful request of clearing the bills without deducting the amounts due from your client towards the material received by him for execution of works.

Your client Mr. Chandrasekhar N. Yadav who is the proprietor of M/s. Ranjana electrical Works and Contractors has been awarded the works of erection of 3.3 KM of 11KV AB (Aerial Bunch) Cable Double Circuit for bifurcation of 11 KV Nagarjuna Signode, 11KV Indo swing, 11KV Rajfoods and 11 KV AB colony feeders emanating from 33/11KV Pragatools Substation in Bowenpally Division of Hyderabad North Circle. The above work was awarded on 28-06-2011 and the agreement was entered into on the same day. All the materials that were required to execute the work have been handed over to your clients on different dates upto the year 2012.

Inspite of receiving all the required material your client has failed to complete major part of the work. The officials of TSSPDCL have been repeatedly addressing letters from the year 2012 onwards to your client demanding that the works should be executed as per the agreement. Inspite of the said letters the major part of the work has not been completed at all.

Your client was awarded another work of erection of 23 numbers 11KV Line AB (Air Break) Switches at various locations of Secunderabad Division in North Circle, Hyderabad. The agreement was entered on 15-02-2011 and the required material was handed over on different dates upto the year 2012.

Inspite of receiving all the required material your client has failed to complete major part of the work The officials of TSSPDCL have been repeatedly addressing letters from the year 2012 onwards to your client demanding that the work should be executed within the time period that is stipulated in the agreement. Inspite of the said letters the major part of the work has not been completed even at all. As the project has been stalled due to the inaction of your client in the interest of the consumers of TSSPDCL the work was got executed by engaging other agencies. The agencies were again issued material to get the work completed.

As your client has failed to execute the above works and has also not returned the material the TSSPDCL as per their internal mechanism has recovered part of the value of the material from the pending bills payable to your client for the other executed works. The said action of TSSPDCL is legal and valid.

As your client has failed to execute the works after entering into agreements, hence repeatedly letters have been issued demanding that the work should be completed or otherwise the proprietary concern shall be blacklisted and as your client has not acted upon the letters and complete the work the proprietary concern has been blacklisted and the proprietary concern and the proprietor i.e, M. Chandrashekar N. Yadav in his personal capacity also cannot bid for any future works.

My client once again reiterates that the allegations made against the Superintending Engineer, Operations, Secunderabad Circle are false and baseless and the said officer has acted lawfully with an interest to protect the revenue of TSSPDCL.

My clients further inform you that they are entitled to proceed against your client and the proprietor Mr. Chandrashekar N. Yadav to recover all the amounts due for the materials supplied from any pending bills and also initiate appropriate civil and criminal legal action for misappropriation of the material and recover the cost of material. Any legal action initiated shall be at the cost of your client.

My clients demand that your client shall have to withdraw the false and baseless allegations made against the Superintending Engineer, Mr. C. Madhav Reddy who has acted in a lawful manner or otherwise my client reserves the right to proceed against your client legally for defaming the officials of TSSPDCL who have acted according to law.

**R. Vinod Reddy**

**Advocate**